## Sheet1
30% PROJECT REVIEW COMMENTS
|  |  |  | 4C - HUDSON (That's so LA)* | 5L - HUDSON (Mattel)** | 5N - HUDSON (Magic Johnson)
1 | COST ESTIMATE |  |  | Not provided | Not provided | Not provided
2 | CONSTRUCTION SCHEDULE |  |  | Not provided | Not provided | Not provided
3 | SITE LOGISTICS PLAN |  |  | Partially provided |  | Not provided
|  | a | Point of entrance locations and traffic routes for movement of the contractor’s work and workers. | Not Indicated | Indicated
|  | b | Escort provisions | Not Indicated | Indicated
|  | c | Defined alterations to existing facilities/infrastructure | Indicated | Indicated
|  | d | Construction zone accommodation of vehicular and aircraft traffic including signage, traffic stripping, flagging, temporary closures, and detours | Not Indicated | Indicated
|  | e | Provisions and plans for worker parking and routes to and from the work | Not Indicated | Indicated
|  | f | Staging/laydown areas for construction equipment, trash/debris receptacles, and material storage and protection | Not Indicated | Indicated
|  | g | Temporary facilities | Partial | N/A
|  | h | Workers/material handling locations and related work zones | Partial | N/A
|  | i | Emergency vehicle access provisions | N/A | N/A
|  | j | Emergency evacuation routes | Indicated on others | Indicated on others
|  | k | Provisions for protection of private and public properties, including leased properties on site, if applicable | Not Indicated | N/A
|  | m | Fencing and enclosure provisions | N/A | N/A
|  | n | Location of off-site, project-related facilities | Not Indicated | Not Indicated
|  | o | Provisions for on-site parking | Not Indicated | N/A
|  | p | Emergency contacts posted on plan | Not Indicated | Not Indicated
|  | q | Defined work shifts and corresponding working hours | Not Indicated | Indicated
|  | r | Routes of temporary utility lines and points of tie-ins | Not Indicated | Not Indicated
|  | s | Provisions for reclamation of areas disturbed by the contractor | N/A | N/A
|  | t | Plans and actions taken to comply with environmental requirements and permits | Not Indicated | Partial
|  | u | Dust/dirt/debris mitigation | Not Indicated | Not Indicated
|  | v | Construction Noise mitigation | Not Indicated | Indicated
4 | PROJECT PHASING |  |  | N/A | N/A | N/A
* | Clearly lable site logistics plans and provide all missing details per above matrix
** | 1) Removing an exterior window will need to be approved by Airport Police and Operations. Special security protocols will need to be employed.
Airport Police can provide details
2) Transporting of material, equipment and rubbish from staging areas to point of work through common use areas within the building will need to occur off hours.
Operations can confirm time frames
3) Indicate on the drawings the footprint and time frame the truck will be staged at the end of the construction chute
4) Indicate on the drawings the footprint needed for the “Heavy Material Delivery” staging area, including space for hoisting equipment

## Sheet2
PROJECT NAME |  |  |  |  | : |  | LAWA PROJECT NUMBER |  |  |  | :
TENANT |  |  |  |  | : |  | DATE |  |  |  | :
COMPANY & AUTHOR OF LOGISTICAL WORK PLAN | [5 empty] | :
[7 empty] | Items to be addressed with 5% Submittal | Items to be addressed in the Logistical work plan submittal (at a minimum) | 100% Conformed | Narrative documenting how & where item is addressed in the logistical work plan (provide reasons for non-conformity; attach separate sheet as necessary)
| 1 | COST ESTIMATE (CONCEPT REVIEW FORM)
| 2 | PROJECT SCHEDULE (CONCEPT REVIEW FORM)
| 3 | UPDATED COST ESTIMATE (100% SUBMITTAL)
| 4 | UPDATED PROJECT SCHEDULE (100% SUBMITTAL)
| 5 | SITE LOGISTICS PLAN - SUBMITTED AS SEPARATE DOCUMENT(S) FROM THE DESIGN DRAWINGS
|  |  | a | Identify point of entrance locations and traffic routes for movement of the contractor’s equipment, materials and workers to the work locations
|  |  | b | Incorporate escort provisions including conformance with LAWA and TSA regulations regarding allowable number and handling of un-badged personnel
|  |  | c | Define alterations to existing facilities/infrastructure
|  |  | d | Locate on plans - construction zone accommodation of vehicular and aircraft traffic including signage, traffic stripping, flagging, temporary closures, barricades, and detours
|  |  | e | Locate on plans - provisions and plans for worker parking and routes to and from the work
|  |  | f | Locate on plans - staging/laydown areas for construction equipment, trash/debris receptacles, and material storage and protection
|  |  | g | Locate on plans - temporary facilities including trailers, dumpsters, and sanitary facilities
|  |  | h | Identify locations and related work zones for worker/material handling equipment such as cranes, and lifts
|  |  | i | Provide emergency vehicle access
|  |  | j | Provide emergency evacuation routes
|  |  | k | Provide protection of private and public properties, including leased properties on site, if applicable
|  |  | l | Identify security provisions
|  |  | m | Locate on plans fencing and enclosure provisions
|  |  | n | Identify location of off-site, project-related facilities
|  |  | o | Identify on-site parking provisions if applicable
|  |  | p | Emergency contacts must be posted on plans
|  |  | q | Define work shifts and corresponding working hours
|  |  | r | Show routing of temporary utility lines and points of connection
|  |  | s | Show provisions for reclamation of areas disturbed by the contractor, if applicable
|  |  | t | Provide plans and actions taken to comply with environmental requirements and permits
|  |  | u | Identify the means for dust/dirt/debris mitigation
|  |  | v | Identify the means for construction noise mitigation
|  |  | w | Incorporate coordination and accommodation of stakeholders impacted by the work
|  |  | x | Incorporate coordination with other contractors impacted by or impacting the work
|  |  | y | Identify any other unique conditions applicable to the project
| 6 | PROJECT PHASING - SUBMITTED AS SEPARATE DOCUMENT(S) FROM THE DESIGN DRAWINGS
|  |  | a | Written description of the work to be accomplished within each phase
|  |  | b | Breakdown the physical elements of the project in maximum thirty (30)-day increments, or less if required to accurately reflect the progression of work, sequenced in accordance with the project schedule
|  |  | c | Include dates for proposed work, daily work hours, and a written work plan for each phase
|  |  | d | The document shall be flexible in its ability to describe real-time updates and shall be updated as required to fully ensure stakeholders are fully informed of revisions as they occur
|  |  | e | The document shall be consistent with the overall Project Schedule
|  |  | f | Indicate on plans the location of barricades, partitions, covered walkways, stairs, scaffolding, work platforms, etc. which are designed to separate construction activities from ongoing operational areas and mitigate disruptions to passenger and other stakeholder traffic flows. Approval must be obtained for Barricade and Enclosure Plans, temporary signage, and Scaffold and Messaging Concept. Please see “Additional Design Standards and Criteria” for a sample presentation. Full-size mock-ups of these systems may be required and agreed to prior to installation
|  |  | g | Identify security provisions
|  |  | h | Identify emergency personnel provisions
|  |  | i | Identify emergency evacuation routes
|  |  | j | Identify egress analysis and occupancy load calculations for each phase of the construction
|  |  | k | Identify the means for public and worker health and safety protection
|  |  | l | Identify any relocation and definition of temporary facilities required to maintain ongoing operations
|  |  | m | State the means for maintenance of fire/life safety systems
|  |  | n | State applicable construction restrictions during special events and holidays
|  |  | o | Identify locations for material stockpiling and staging
|  |  | p | Identify locations and related work zones for worker/material handling equipment
|  |  | q | Identify the plan for rubbish removal, including location of trash bins
|  |  | r | Identify modification and maintenance of existing systems during construction
|  |  | s | Identify temporary signage/way-finding devices
|  |  | t | Identify stakeholder relocations
|  |  | u | Show routing of temporary utilities, lines, and points of connection
|  |  | v | Identify temporary facilities
|  |  | w | Identify means of dust/dirt/debris mitigation
|  |  | x | Identify means of construction noise mitigation
|  |  | y | Identify any other unique conditions applicable to the project